## Schedule as of Spring
|  |  |  | Summer 2021 | [8 empty] | Fall 2021
| Task |  | Summer |  | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06
1 Complete Senior Research Project
1.1 Aquire Data Set | bar: 2021-08-23
1.2 Develop & Test Code | bar: 2021-08-23 to 2021-10-11
|  | 1.2.1 Develop & Test convoluation part with 3x3 Sobels operator filter |  |  | 2021-08-30: PR 1; 2021-09-13: PR 2
|  | 1.2.1b Develop NN code |  |  | 2021-09-13: PR 2
1.2.2 Develop & Test cnn with 2x2 roberts cross filter | bar: 2021-09-27
|  | 1.2.3 Develop & Test cnn with 4x4 Prewitt operator filter |  |  | 2021-09-27: PR 3
[13 empty] | PR 4 |  | PR 5
| 1.3 Testing code with large dataset for functionailiy and testing for accuracy of actual filters |  |  |  | 2021-11-15: Presenations
| 1.7 Final Presentation |  |  |  | 2021-11-22: Poster
| 1.8 Update Poster |  |  |  | 2021-11-29: Final Paper
1.9 Write Final Paper
TASK DETAILS
1.1 Aquire Data Set
The data for these experiments will come from the online repository at https://susanqq.github.io/UTKFace/
1.2 Develop & Test Code
The cnn code will be developed in Python and tested for filters set 1 - 3 using a few parts of dataset to test functionality
1.2.1 Develop & Test cnn with 3x3 Sobels operator filter
1.2.2 Develop & Test cnn with 2x2 roberts cross filter
1.2.3 Develop & Test cnn with 4x4 Prewitt operator filter
1.3 Testing code with large dataset for functionailiy and testing for accuracy of actual filters
Will be run with fixed conditions such as one convolution layer, max pooling, ReLU, sigmoid activation, one hidden layer etc...
Progress Report Topics
P.R. 1
Discuss data acquisition
show progress on cnn functionality
P.R. 2
Hopefully done with initial 3x3 filter cnn and show functionality
P.R. 3
finished 3x3 filter
show progress alternating to 2x2/4x4 kernals
P.R. 4
finished other filters code,
begin testing large dataset for accuracy for each
P.R. 5
discuss results and next steps